## Sheet1
| PC1 | PC2 |  | 1-ttc | 1-est | 1-eft | 2-ttc | 2-est | 2-eft | slack
A-Harolds House of Bottles | 5 | 13 | A-Harolds House of Bottles | 5 | 0 | 5 | 13 | 5 | 18 | 5
B-E Z Shop Car Wash | 3 | 9 | B-E Z Shop Car Wash | 3 | 5 | 8 | 9 | 18 | 27 | 0
C-Steinbaugh's Boats and Motors | 12 | 7 | C-Steinbaugh's Boats and Motors | 12 | 8 | 20 | 7 | 27 | 34 | 0
D-Bi State Auto Supply | 7 | 9 | D-Bi State Auto Supply | 7 | 20 | 27 | 9 | 34 | 43 | 0
E-Jake's Bar and Grill | 9 | 10 | E-Jake's Bar and Grill | 9 | 27 | 36 | 10 | 43 | 53 | 0
F-Hanson Agency Insurance | 11 | 3 | F-Hanson Agency Insurance | 11 | 36 | 47 | 3 | 53 | 56 | 0
G-Taylor Shoe | 1 | 3 | G-Taylor Shoe | 1 | 47 | 48 | 3 | 56 | 59 | 0
[10 empty] | 5 | 5
|  |  | ONE Possible Johnson's Rule Sequence | G-Taylor Shoe | B-E Z Shop Car Wash | A-Harolds House of Bottles | D-Bi State Auto Supply | E-Jake's Bar and Grill | C-Steinbaugh's Boats and Motors | F-Hanson Agency Insurance
|  |  |  | 1-ttc | 1-est | 1-eft | 2-ttc | 2-est | 2-eft | slack
|  |  | G-Taylor Shoe | 1 | 0 | 1 | 3 | 1 | 4 | 1
|  |  | B-E Z Shop Car Wash | 3 | 1 | 4 | 9 | 4 | 13 | 0
|  |  | A-Harolds House of Bottles | 5 | 4 | 9 | 13 | 13 | 26 | 0
|  |  | D-Bi State Auto Supply | 7 | 9 | 16 | 9 | 26 | 35 | 0
|  |  | E-Jake's Bar and Grill | 9 | 16 | 25 | 10 | 35 | 45 | 0
|  |  | C-Steinbaugh's Boats and Motors | 12 | 25 | 37 | 7 | 45 | 52 | 0
|  |  | F-Hanson Agency Insurance | 11 | 37 | 48 | 3 | 52 | 55 | 0
1
At a minimum.
I need to see your optimal sequence in the body of your summary (maybe a Table not just within the dialogue and by job name) and you need to discuss it with regard to time in the system (55) and idle time (1).
There needs to be a discussion of how this sequence is a better sequence than just taking the jobs as they come.
I need to see a Gantt Chart for the optimal sequence.
The write up needs to have structure (section headers and organized thoughts), flow well, and have a conclusion/recommendation section with actual recommendations and numbers.
|  |  |  | PC1 |  | PC2
|  |  | G-Taylor Shoe | 1 | IDLE2 | 1
|  |  | B-E Z Shop Car Wash | 3 | G-Taylor Shoe | 3
|  |  | A-Harolds House of Bottles | 5 | B-E Z Shop Car Wash | 9
|  |  | D-Bi State Auto Supply | 7 | A-Harolds House of Bottles | 13
|  |  | E-Jake's Bar and Grill | 9 | D-Bi State Auto Supply | 9
|  |  | C-Steinbaugh's Boats and Motors | 12 | E-Jake's Bar and Grill | 10
|  |  | F-Hanson Agency Insurance | 11
IDLE1 is a place holder to balance out the lengths of the Gantt Chart. |  |  | IDLE1 | 7 | C-Steinbaugh's Boats and Motors | 7
With IDLE PC1 is then length 55 and PC2 is length 55.
| GANTT CHART |  |  |  | F-Hanson Agency Insurance | 3